## DetailedSchedule_Rev0.1
SPS - Detailed Schedule
Schedule plan revised: 04 Mar 2022
Spare Part System (SPS) |  | 2021/2022
|  | 10 | [6 empty] | 10 | [6 empty] | 11 | [29 empty] | 12 | [30 empty] | 1 | [30 empty] | 2 | [27 empty] | 3
Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Software Development
Study web design using ASP.net MVC | bar: 10 25 to 10 29; 11 1 to 11 2; 11 8 to 11 12; 11 15 to 11 19; 11 22 to 11 26; 11 29 to 12 1
UI Design | bar: 12 2 to 12 3; 12 6 to 12 10; 12 13 to 12 17; 12 20 to 12 24; 12 27 to 12 31
Database design | bar: 1 3 to 1 7; 1 10 to 1 14; 1 17; 1 19 to 1 22; 1 24 to 1 28
System design (Product Spec) | bar: 2 4 to 2 5; 2 7 to 2 11; 2 14 to 2 18
Integrated test (IT) and system test (ST) | bar: 2 21 to 2 25; 2 28
Trial run | bar: 3 1 to 3 4; 3 7 to 3 11; 3 14 to 3 18; 3 21 to 3 22; 3 24 to 3 25; 3 28 to 3 31
| Plan | 10 4: Legend:
Actual
Rest day
Rev0.1
| Visitor Management System 2 (VMS 2) | 10 1: 2019
|  | 8 | [30 empty] | 9 | [29 empty] | 10
| Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Software Development
DP | bar: 8 8 to 8 9
UI Design | bar: 8 8 to 8 9; 8 13
Specification for Approval (customer) | bar: 8 13 to 8 15
DR0 - UI Design Review | bar: 8 16
Database design | bar: 8 16 to 8 17
System design | bar: 8 16 to 8 17; 8 19
Software design, programming and UT (Unit Test) | bar: 8 20 to 8 23; 8 26 to 8 30; 9 3 to 9 6
IT (Integrated Test) | bar: 9 10 to 9 12
ST (System test) | bar: 9 13; 9 17 to 9 19
AQ0 - Design Completion Review | bar: 9 20
QA evaluation | bar: 9 23 to 9 26
AQ2 - Deliver Approval | bar: 9 27
User Acceptance Test | bar: 9 30 to 10 4; 10 7 to 10 11
AQ2-2 - Final Decision | bar: 10 14
[5 empty] | Legend: |  |  |  | ♦ | Plan |  |  | ♦ | Actual
[100%]
[100%]
Note on C40: Deborah Lim Shin Fei: Includes documentation
Note on C41: Deborah Lim Shin Fei: Product specification Software design specification

## To-Do List
To-Do List
No. | Application | Function |  | Spec | PIC | Completion Date | Complete % | Status
|  | Main | Sub
1 | SPS Client | Record | Record Transfer | Refer SPS Product Spec(Rev0.0x).xlsx *latest version | Azmir | 2023-02-24 | 100% | Completed
|  |  | Import Record - Transfer |  | Azmir | 2023-03-03 | 100% | Completed
3 |  | Report | In/Out Record - Transfer |  | Azmir | 2023-03-09 | 100% | Completed
4 |  | Maintenance | Part - Minimum part quantity |  | Azmir | 1900-03-10 | 100% | Completed
5 | SPS Server | Sent email for part status to administrator | - |  | Azmir | 2023-03-17 | 100% | Completed
[6 empty] | Complete % | 100%